## Sheet1
RIDA TITLE | Descpription | Type | Draft Or Officail RIDA | RIDA ID
Change the process for deceased accounts |  |  | Draft
CRM 7 Order Management (R1) | Need to identify impact to BOS of any work order or work center changes that are being made | Decision | Active in ADO | 687234
Flow of Integrations from S/4 or direct to Service Cloud V2 | Direct Integrations from CRM to a 3rd Party // flowing through ECC No Direct from CRM to any system, all are VIA ECC ECC |  | Draft
Service Order vs. Notifications Decisions will need to happen with WAM team |  |  | Draft
Removing Meter Data from Contract Management | Decision to Remove Meter Data from Contract Management - New Contracts Screen - Cover in MIMO Workshop - Remove Photo read option | Decision | Draft
Case Management | Decision required to create an EMMA case vs a service notification wherever needed |  | Draft
Cleaning Up Contract Management |  |  | Draft
Service Notifications | Build App or S/4 Creating Service Order | Decision | Draft
All outside links |  |  | Draft
Notes in GUI | Notes are being stored in GUI at the table level and translation will have to take place (5 standard tables in CRM) |  | Draft
Migration from CRM7 to Service Cloud Directly | Interaction Records, Contract Management, Owner Allocation From BPML: o Overview o Categorization o Organizational Data o Partner o Transaction History o Follow-up o Actions o Follow-up Details o Activity Clipboard o Create Followup o Notes History o Last Intractions o Correspondence o Contacts |  | Draft
Display Service Notificaiton: Elec Investigation | Where are we going to build to logic / where the work will reside Main work center popilated based on the notification |  | Draft
Inbound / Outbound Emails | Riverstar, Forms, etc. |  | Draft
Forms (Currently in CRM7 and Riverstar) | Need to make a decision where we are going to have all of the forms (Currently that forms drop down is both in CRM and Riverstar |  | Draft
Org Structure in CRM | (Cross-functional with P&C) Emma cases, refunds, how they're going to get thia back to SAP |  | Draft
Mapping questions to each order CRM Order Management | Need to decide on best approach |  | Draft
If we have a 911 script it must be concise | Potentially integrate with 911 option to use API with S/4 to submit orders |  | Draft
Decision needed on Build App or S/4 for Creating Service Order |  |  | Draft
Service Notifications |  |  | Draft
8mil in KAN1, 7.1 in BUT --> Everything missing in BUT will be created in KAN1 | SNP / CVI will handle this | Change Gap --> WRICEF | Draft
Removing Tile Option | Majority of group decided we will likely want to remove the title option for Future State. There have been many issues in current state with customers not being identified with the correct title. | Decision | Draft
Removing BP ID in Dev | Potential decision to remove BP ID in Config system so SNP doesn't carry it over | Decision | Draft
PO Box Fields in CRM7 | Need to check if there are PO Boxes that are utilizing fields in CRM7, need to determine if we need this for future state. (DQM is not validating these fields) @DAWN M PETTENGILL and @Shibu Devapalan Prabha Ajay confirmed: Private PO Box Field is currently being used so will need that for the future state | Decision | Draft
Do we need to show VAPS Marketing Program for Agents in Service Cloud? |  | Decision | Draft
Potential Decision to Change the BDEX and EMA Case Routing. (Need more details) |  | Decision | Draft
Loading Cases into Service Cloud V2 | Need to understand what notifications are going to be changed to cases Not loading cases into Service Cloud (in-flight complaint is a current pain point) Open complaints --> notification to case Look if there are open or in progress notifications in current state Need to Strategize Cut-off period for loading (is it 6 yrs?) | Decision | Draft
Do any or all roles require FACTA validation during change BP | Not all roles in CRM run FACTA in change BP | Decision | Draft
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Line 6 will need clarification and discussion - photo read? which meter data was decided to be removed?