## Response Tracker
Client Name: SMUD |  |  |  |  | Status:
Bid Title: SYSTEM INTEGRATOR FOR TIME OF DAY (TOD) RATE CHANGE AUTOMATION |  |  |  |  | Open
Drafted
Submission Due Date: 27th April 2017 |  |  |  |  | Ready for Review
Responsibility Matrix as of 6th April 2017 |  |  |  |  | Complete
Section |  | Section Name | Owner | Reviewer | Status | Date | Comments | Instructions
6.1 |  | Proposal Agreement | Veronica | Geoff | Open | 12th April
6.2 |  | Safety Compliance Certificate | Veronica | Geoff | Open | 12th April
6.3 |  | Non Collusion Statement | Veronica | Geoff | Open | 12th April
6.4 |  | Public Record Indemnity Agreement | Veronica | Geoff | Open | 12th April
6.5 |  | Prompt Payment Program | Veronica | Geoff | Open | 12th April
6.6 |  | Seed Program Small Business Declaration | Veronica | Geoff | Open | 12th April
6.7 |  | Designation of Prime Contractor, Subcontractors and Suppliers | Veronica | Geoff | Open | 12th April
6.8 |  | Detailed Proposal
| 6.8.1 | Evaluation Criteria 1 (Mandatory Pass/Fail requirements) | Veronica | Geoff | Open | 12th April
| 6.8.2 | Evaluation Criteria 2 (SEED Program Evaluation points) | Veronica | Geoff | Open | 12th April
| 6.8.3 | Evaluation Criteria 3 (Proposer's & Project Team's Experience, Methodologies, Implementation Capability)
| A | List of 3 former clients for projects of similar nature | Veronica | Matt | Open | 12th April
| B | Origin, Background and the Size of the Proposer's Company and Division who wll run this Project | Veronica | Matt | Open | 12th April
| C | Proposer's and the proposed team's previous electric utility experience | Veronica | Matt | Open | 12th April
| D | Corporate and Project Organization chart | Veronica | Matt | Open | 12th April
| E | Resumes of Key Individuals on the proposed Organization chart | Veronica | Matt | Open | 12th April
| F | Describe 3 full time implementations or upgrades for each core team member who will comprose the Rate Change Automation project team | Matt | Eva | Open | 12th April
| G | The Proposer must ensure in writing, that to the extent within its control, the personnel proposed to work on this project shall remain available to the project for the full term of the contract. Please also describe how you propose to ensure your core team member continuity? | Matt | Eva | Open | 12th April
| H | Please describe the skill set, number of staff (FTE) for both IT and Process Resource skill sets, and approximate amount of hours of SMUD staff needed for the project. | Matt | Eva | Open | 12th April
| I | Provide the name(s) of each organization with which you will be partnering and the purpose of the partnership. Describe the history of the partnership, current clients supported through this partnership, and services provided by each partner. | Matt | Eva | Open | 12th April
| J | Detail out your approach, staffing and staff availability during preparation for go-live and after go-live. | Matt | Eva | Open | 12th April
| K | Please provide a description of the Proposer's expertise in the area(s) as described in the Scope of Services of this Request for Proposal, including but not limited to workflow management, and automating rates & billing processes within SAP and CRM. Specifically address the three projects that meet Mandatory Pass/Fail Requirement No. 1 (Section 6.8.1) | Matt | Eva | Open | 12th April
| L | Describe one implementation of a rate based solution where customers were billed from MDUS enabled meters. Describe the process of enrolling the customer on a rate. | Matt | Eva | Open | 12th April
| M | Please provide a description of the Proposer’s previous experience related to rate automation and workflow processes supporting billing changes as described in the Scope of Services of this Request for Proposal. | Matt | Eva | Open | 12th April
| N | Describe how you will help SMUD meet its goals for operational efficiency, business process improvements and elimination of manual workflow processes when implementing these set of requirements in the following areas. <Please refer RFP for more details> | Matt | Eva | Open | 12th April
| O | Please identify the existing business processes and workflows that you expect will be impacted by the implementation of rate change automation, and describe your approach to identify and update those processes and workflows that will need to be updated. | Matt | Eva | Open | 12th April
| P | Provide an example of an approved detailed design document on an SAP Implementation performed. | Matt | Eva | Open | 12th April
| Q | Describe your experience (implementation approach, collaboration experience with other clients, what was accomplished, and lessons learned) of SAP implementation specific to the electric utility sector. | Matt | Eva | Open | 12th April
| R | Please include a narrative description of how the Proposer will organize and perform the services as described in the Scope of Work of this Request for Proposal. | Matt | Eva | Open | 12th April
| S | Please describe how you will work with SMUD to ensure that the engagement of contracted resources will be managed to deliver optimum performance <Please refer RFP for more details> | Matt | Eva | Open | 12th April
| T | Provide a detailed project schedule and align the schedule with the personnel resources that will be needed (yours and SMUD), and the assumptions you used to arrive at this schedule. Identify any risks associated with the schedule. | Matt | Eva | Open | 12th April
| U | Describe your project management approach for successfully implementing this project and accomplishing SMUD’s goal set forth in this RFP and business requirements. | Matt | Eva | Open | 12th April
| V | Describe in detail your proposed change management strategy for this project. Include your thoughts on how change management compliments and/or interacts with other project activities. | Matt | Eva | Open | 12th April
| W | Please provide your proposed schedule for the Rate Change Automation project that includes milestones, key deliverables, all resource requirements (including SMUD), and estimated timelines for the proposed SAP rate change automation and related workflow processes and reporting implementation at SMUD. Please document all assumptions made in developing the project plan. <Please refer RFP for more details> | Matt | Eva | Open | 12th April
| X | Describe your proposed communication strategy for this project. | Matt | Eva | Open | 12th April
| Y | Describe your issue tracking methodology and process for resolution and issue escalation. | Matt | Eva | Open | 12th April
| 6.8.4 | Evaluation Criteria 4 Functional & Technical Requirements - Core Features and Functionality
| A | Describe the standard features provided in SAP and note which features will be enabled to meet our stated project objectives within the project scope and requirements document. | Eva | Matt | Open | 12th April
| B | Describe the features that do not exist as standard SAP or CRM features and functionalities which will require customization(s) to meet our stated project objectives within the project scope and requirements document. | Eva | Matt | Open | 12th April
| C | Describe your proposed solution on how to design, develop and incorporate a Rate Change repository into the rate selection and billing workflow processes, and also use for workflow management purposes. | Eva | Matt | Open | 12th April
| D | Describe your proposed solution on how to design, develop and incorporate the PEV repository into the rate selection and billing processes, and track updates/changes to PEVs. | Eva | Matt | Open | 12th April
| E | Describe your proposal for the design and/or functionality of the PEV repository to support a future re-certification or verification process, which may include external interfaces. | Eva | Matt | Open | 12th April
| F | Describe the proposed solution’s use of role based security and use of SAP security roles. | Eva | Matt | Open | 12th April
| G | Describe your approach for the design and development of a mass rate selection and upload feature of existing customers transitioning customers from their current rate to a new rate. Be sure to explain how this can impact other utility business processes. | Eva | Matt | Open | 12th April
| H | Discuss the top challenges you encountered in your past implementations of automated rate and billing workflow management solutions. Describe in detail how these challenges were resolved. Include how challenges were discovered, if resolution occurred before implementation or after implementation, the impacts these challenges had on the overall implementation, and the lessons learned. | Eva | Matt | Open | 12th April
| I | Based on the scope of work described in this RFP and business requirements, and your experience implementing similar projects, describe any challenges and/or risks you anticipate in implementing this project. Include risk mitigation steps you would take to minimize the risks. | Eva | Matt | Open | 12th April
| J | Describe your proposed method of storing and leveraging rate change and PEV historic and active data in SAP for purposes of eligibility rules, reporting, audit trails and interfaces. | Eva | Matt | Open | 12th April
| K | Describe your proposed solution on how to configure the workflow management reporting solution specific to this RFP and business requirements. | Eva | Matt | Open | 12th April
| L | Describe your proposed solution on how to address the reporting needs specific to this RFP using standard or customized SAP solutions. | Eva | Matt | Open | 12th April
| M | Describe how your solution will be designed to increase operational efficiencies and existing reporting and tracking capabilities, and provide accurate and consistent quality data within SAP and CRM. | Eva | Matt | Open | 12th April
| N | Describe how your proposed solution can increase process and data visibility and support SMUD’s Enterprise Data Governance Program. | Eva | Matt | Open | 12th April
| O | Describe how your proposed solution will improve exception processing for billing and rate changes, including alerts and tracking for workflow management. Include how, if any, of the reporting or tracking will be managed within SAPs BPEM module. | Eva | Matt | Open | 12th April
| P | Describe your approach to on-the-job training of SMUD developer and functional staff during the project to understand the solution. Include the approach for updating and creating detailed training documents. | Eva | Matt | Open | 12th April
| Q | Describe in detail the roles of analysts, developers, and/or base team members in validating properly operating interfaces with the web, repositories and automated process flows in CRM and SAP. Describe the documentation and training that will be provided to IT staff and how it will address the process for any future updates made to the customized solution to ensure the processes remain whole and functional. | Eva | Matt | Open | 12th April
| R | Describe your Test metrics and defects tracking and resolution process. | Eva | Matt | Open | 12th April
| S | Describe your approach for the regression testing of existing custom objects in SAP and CRM, such as batch processes, workflows, etc.. | Eva | Matt | Open | 12th April
| T | Describe your post go-live support strategy. | Eva | Matt | Open | 12th April
| U | Describe your training methodology and strategy. Describe how you plan to incorporate SMUD feedback in any training documentation. | Eva | Matt | Open | 12th April
| V | Describe your testing methodology and strategy for all phases of testing (unit, integration, system, data integrity, regression, performance and UAT). Include your approach for development test strategies, test cases and test scripts for the multiple phases. | Eva | Matt | Open | 12th April
| W | Discuss your expectations for use of the sandbox, development and QA environments. | Eva | Matt | Open | 12th April
| 6.8.5 | Evaluation Criteria 5: Commercial Terms (Price) and Compliance with SMUD's Contractual Terms
|  | A. This section includes the cost information contained in the Bid Schedule section of this Request for Proposal. B. The Proposer shall note all exceptions taken to this Request for Proposal including the contract terms and conditions of the contract included in the Sample Contract section of this Request for Proposal. SMUD reserves the right to reject any proposal based on noncompliance with the attached contract terms and conditions. | Eva | Cory | Open | 12th April
6.9 | 6.9 | Bid Schedule |  |  | Open | 12th April

## Production Instructions
No | Subject | Input
1 | Client Name | SMUD
2 | RFP / Proposal Title | SYSTEM INTEGRATOR FOR TIME OF DAY (TOD) RATE CHANGE AUTOMATION
3 | RFP No. | 170061.MP
4 | Client Submission Date / Time | 5:00 P. M., Local Time (Sacramento, CA) Thursday, April 27, 2017
5 | Target Production Submission
6 | Number of Hardcopies | SUBMIT ONE (1) COPY OF THE PROPOSAL IN HARD COPY AND ONE (1) IN ELECTRONIC (ON FLASH DRIVE) FORMAT. ADDITIONALLY, THE PROPOSER SHALL SUBMIT ONE HARD COPY JUST OF SECTION 6.8, DETAILED PROPOSAL, AND ONE COPY OF THAT FILE ON THE FLASH DRIVE.
7 | Number of Softcopies (CD)
8 | Number of Softcopies (Flash drive)
9 | Email softcopy to
10 | Addressed to (labels for envelope etc)
11 | HCL Account Executive
12 | Banner (client website)

## Bid Calendar
Action Item | Date